## Sheet1
Activity ID | Key Milestone | Detailed Activities | Estimated Time (Hours) | Target Completion | Status
A1 | Data Connection & Preparation | Connect to dummy data source, perform initial data cleaning and shaping within Tableau. | 4 | End of Day 1 (June 2) | Completed
A2 | Data Model & Relationships | Define relationships between tables, create calculated fields for initial data transformation. | 1 | End of Day 1 (June 2) | Completed
A3 | Core Measures & Dimensions | Identify and set up key measures and dimensions | 2 | End of Day 1 / Start of Day 2 | Completed
A4 | Calculated Fields & Parameters | Develop complex calculated fields for KPIs | 2 | End of Day 2 (June 3) | Completed
A5 | Dashboard Design & Visualizations | Create all required dashboard sheets, build appropriate chart types apply filters and actions. | 5 | End of Day 2 (June 3) | Completed
A6 | Performance Tuning & User Experience | Optimize workbook performance, refine dashboard layouts | 1 | End of Day 2 (June 3) | Completed
A7 | Publishing & Sharing | Prepare workbook for local demonstration | 1 | Morning of Day 3 (June 4) | Completed
A8 | Case Study Discussion & Demo | Present the Tableau dashboard and discuss insights. | N/A | Day 3 (June 4) | Scheduled

## Sheet2
KPI / View | Section | KPIs | Meaures | Calculculated Field | Filters Needed | Preferred Interactive Chart Type | Attributes Used (Directly from Dataset) | Derived Attributes (and their Source)
4. Cost per Patient by Indication – show cost variations, with filters for payer type and provider type. | Operational Efficiency & Cost | Cost per Patient by Indication | Average Cost per patient, Total Cost of Care | Select Breakdown, Breakdown Dimension, Dynamic Title | Payer Type, Provider Type | Bar Chart (for averages) or Box Plot (for distribution/variations) | PatientID, Indication, Cost, PayerType, ProviderType
5. Readmission Rate by Indication – Heatmap, filtered by age group and ethnicity. | Operational Efficiency & Cost | Readmission Rate by Indication | Readmission Rate | Select Breakdown, Breakdown Dimension, Dynamic Title | Age Group, Ethnicity | Heatmap (as specified) | PatientID, Indication, Ethnicity, IsReadmissionFlag, DateOfBirth | AgeGroup (from DateOfBirth)
6. Length of Stay by Treatment – showing hospital stay durations, filtered by payer type and age group. | Operational Efficiency & Cost | Length of Stay by Treatment | Average Length of Stay | Select Breakdown, Breakdown Dimension, Dynamic Title | Payer Type, Age Group | Box Plot (for distribution) or Bar Chart (for average) | Treatment, PayerType, AdmissionDate, DischargeDate, DateOfBirth | LengthOfStayDays (from DischargeDate - AdmissionDate), &lt;br> AgeGroup (from DateOfBirth)
1. Patient Distribution by Indication – by age group, ethnicity, and payer type. | Patient Demographics & Journey | Patient Distribution by Indication | Patient Count, Top Indication | Select Breakdown, Breakdown Dimension, Dynamic Title | Age Group, Ethnicity, Payer Type | Bar Chart (Stacked/Grouped) or Treemap | PatientID, Indication, Ethnicity, PayerType, DateOfBirth | AgeGroup (from DateOfBirth)
2. Patient distribution by treatment -by age group, ethnicity, and payer type. | Patient Demographics & Journey | Patient distribution by treatment | Average Age, Top Treatment | Select Breakdown, Breakdown Dimension, Dynamic Title | Age Group, Ethnicity, Payer Type | Bar Chart (Stacked/Grouped) or Treemap | PatientID, Indication, Treatment, Ethnicity, PayerType, DateOfBirth | AgeGroup (from DateOfBirth)
3. Treatment Success Rate by Indication – comparing success rates across treatments, filtered by pharmacy type. | Treatment Effectiveness & Outcomes | Treatment Success Rate by Indication | Success Rate | Treatment Success Rate,Dynamic Title | Pharmacy Type | Bar Chart (for comparison) or Bullet Chart (if targets/benchmarks exist) | Indication, Treatment, PharmacyType, TreatmentOutcome | TreatmentSuccessFlag (e.g., TRUE if TreatmentOutcome is 'Resolved' or 'Improved')
7. Treatment Efficacy Comparison – comparing different treatments, with filters for provider type and ethnicity. | Treatment Effectiveness & Outcomes | Treatment Efficacy Comparison | Treatment Success Rate, Top Performing Tratment | Select Breakdown, Breakdown Dimension, Dynamic Title | Provider Type, Ethnicity | Bar Chart (for direct comparison) or Scatter Plot (if multiple variables) | Treatment, ProviderType, Ethnicity, TreatmentOutcome | EfficacyScore (e.g., numerical mapping from TreatmentOutcome values like 'Resolved' = 10, 'Improved' = 8)
8. Mortality Rate by Treatment – displaying mortality trends, filtered by indication and provider type. | Treatment Effectiveness & Outcomes | Mortality Rate by Treatment | Mortality Rate Rate, Lowest Mortality Treatment | Select Breakdown, Breakdown Dimension, Dynamic Title | Indication, Provider Type | Line Chart (for trends) or Area Chart | Treatment, Indication, ProviderType, PatientDisposition | MortalityFlag (e.g., TRUE if PatientDisposition is 'Deceased')

## Sheet3
Attribute Name | Description | Data Type | 01_Indication
PatientID | A unique number for each patient. | Numeric | 1.1_PatientCount
Indication | The main health condition a patient has. | String/Text | 1.2_TopIndication
DateOfBirth | The patient's birth date. | Date&Time | 2.0_Treatment
Ethnicity | The patient's ethnic background. | String/Text | 2.1_AvgAge
PayerType | How the patient's care is paid for | String/Text | 2.2_TopTreatment | *1_Patient Demographics
Treatment | The specific care or medication given to the patient. | String/Text | 3.0_SuccessRate | *2_Operational Efficiency
PharmacyType | Where the patient's prescriptions were filled. | String/Text | 3.1_SuccessRate | *3_Treatment Effectiveness
ProviderType | The type of place or specialist that provided care. | String/Text | 4.0_Cost
AdmissionDate | The date the patient entered the facility for this visit. | Date&Time | 4.1_TotalCost
DischargeDate | The date the patient left the facility for this visit. | Date&Time | 4.2_AvgCost
Cost | The total expense for this patient's treatment episode. | Numeric Currency | 5.0_Readmission
TreatmentOutcome | The result of the treatment | String/Text | 5.1_ReadRate
PatientStatus | The patient's status when discharged | String/Text | 6.0_LengthOfStayDays
IsReadmissionFlag | TRUE if the patient was readmitted shortly after a previous discharge. | Boolean | 6.1_AvgLength
7.0_TreatmentEfficy
7.1_TopPerf
8.0_Mortality
8.1_MorRate
8.2_LowestMor

## Sheet4
PatientID | PatientID,Indication,DateOfBirth,Ethnicity,PayerType,Treatment,PharmacyType,ProviderType,AdmissionDate,DischargeDate,Cost,TreatmentOutcome,PatientDisposition,IsReadmissionFlag, 1,High Blood Pressure,1965-03-12,White,Commercial,Diet & Exercise,Retail,Clinic,2023-01-05,2023-01-08,1200.50,Success,Discharged,No, 2,Diabetes,1978-07-20,Black,Medicare,Pills,Hospital,Specialist,2023-02-10,2023-02-15,2500.75,Success,Discharged,No, 3,Asthma,2005-11-01,Hispanic,Medicaid,Inhaler,Retail,Specialist,2023-03-15,2023-03-17,800.00,Success,Discharged,No, 4,High Blood Pressure,1950-09-25,Asian,Commercial,Pills,Retail,Clinic,2023-04-01,2023-04-03,950.00,Success,Discharged,No, 5,Arthritis,1972-01-30,White,Commercial,Phys Therapy,Retail,Specialist,2023-05-20,2023-05-22,950.25,Success,Discharged,No, 6,Depression,1990-06-18,Black,Medicaid,Talk Therapy,N/A,Specialist,2023-06-01,2023-06-03,700.00,Success,Discharged,No, 7,Diabetes,1948-02-05,White,Medicare,Pills,Hospital,Specialist,2023-07-10,2023-07-15,2800.00,Success,Discharged,Yes, 8,Migraine,1985-10-03,Hispanic,Commercial,Pain Pills,Retail,Specialist,2023-08-22,2023-08-23,400.00,Success,Discharged,No, 9,High Blood Pressure,1960-04-12,Asian,Medicare,Diet & Exercise,Retail,Clinic,2023-09-01,2023-09-03,1100.00,Success,Discharged,No, 10,Diabetes,1995-12-08,White,Commercial,Insulin,Specialty,Specialist,2023-10-14,2023-10-16,3500.00,Success,Discharged,No, 11,High Blood Pressure,1970-02-28,Black,Medicaid,Pills,Retail,Clinic,2023-11-01,2023-11-04,1100.00,Success,Discharged,No, 12,Diabetes,1968-09-15,White,Medicare,Pills,Hospital,Specialist,2023-12-05,2023-12-10,3000.00,Success,Discharged,Yes, 13,Asthma,2010-04-20,Asian,Commercial,Inhaler,Retail,Specialist,2024-01-01,2024-01-03,750.00,Success,Discharged,No, 14,High Blood Pressure,1955-08-10,Hispanic,Medicaid,Diet & Exercise,Retail,Clinic,2024-02-15,2024-02-17,850.00,Success,Discharged,No, 15,Arthritis,1963-03-05,Black,Commercial,Pain Relief,Retail,Specialist,2024-03-10,2024-03-12,850.00,Success,Discharged,No, 16,Depression,1988-11-25,White,Medicare,Pills,N/A,Specialist,2024-04-01,2024-04-05,1000.00,Success,Discharged,No, 17,Pneumonia,1935-01-01,Asian,Medicare,Oxygen,Hospital,Hospital,2024-05-20,2024-05-28,7500.00,Failure,Expired,N/A, 18,Diabetes,1992-07-07,Black,Commercial,Pills,Retail,Specialist,2024-06-10,2024-06-12,2100.00,Success,Discharged,No, 19,Kidney Disease,1975-04-01,White,Medicaid,Diet,N/A,Specialist,2024-07-01,2024-07-03,600.00,Success,Discharged,No, 20,High Blood Pressure,2000-09-10,Hispanic,Commercial,Pills,Retail,Clinic,2024-08-01,2024-08-03,980.00,Success,Discharged,No, 21,High Blood Pressure,1958-06-01,White,Medicare,Pills,Retail,Clinic,2024-09-01,2024-09-03,900.00,Success,Discharged,No, 22,Diabetes,1980-11-11,Asian,Commercial,Pills,Retail,Specialist,2024-10-10,2024-10-14,2200.00,Success,Discharged,Yes, 23,Asthma,2000-03-03,Black,Medicaid,Inhaler,Hospital,Specialist,2024-11-01,2024-11-05,1200.00,Success,Discharged,No, 24,Heart Disease,1962-07-22,White,Medicare,Bypass Surgery,Hospital,Hospital,2024-12-01,2024-12-10,30000.00,Success,Discharged,No, 25,Arthritis,1970-05-15,Hispanic,Commercial,Shots,Retail,Specialist,2025-01-05,2025-01-07,1500.00,Success,Discharged,No, 26,Depression,1998-02-10,Asian,Medicaid,Pills,N/A,Specialist,2025-02-01,2025-02-03,650.00,Success,Discharged,No, 27,Pneumonia,1940-10-01,Black,Medicare,Ventilator,Hospital,Hospital,2025-03-10,2025-03-25,9000.00,Failure,Expired,N/A, 28,High Blood Pressure,1982-04-05,White,Commercial,Diet & Exercise,Clinic,Clinic,2025-04-15,2025-04-16,700.00,Success,Discharged,No, 29,Diabetes,1968-09-20,Hispanic,Medicare,Pills,Hospital,Specialist,2025-05-01,2025-05-07,2700.00,Success,Discharged,No, 30,Heart Disease,1990-01-25,Black,Medicaid,Stent,Hospital,Hospital,2025-06-01,2025-06-04,10000.00,Success,Discharged,No,
Indication
DateOfBirth
Ethnicity
PayerType
Treatment
PharmacyType
ProviderType
AdmissionDate
DischargeDate
Cost
TreatmentOutcome
PatientDisposition
IsReadmissionFlag